## Sheet1
Task S.no 1	Task name	Description	Other Comments/Status	Task Start Date	Task End Date	Hours spent
1	Cloud sql proxy ticket number INFRA 2652	Review usage for CPU & memory in Cloud Monitoring metrics explorer. Look at the historical usage (1 month at least) and note the maximum amount of CPU and memory used by the cloudsql-proxy containers	As part of security alerts we've discovered that `cloudsql-proxy` container has no requests/limits specified (it only has `cpu: 100m` set. According to the documentation [1] "The proxy's memory use scales linearly with the number of active connections" which means we can't use hardcoded values for all cases. This task is to observe pods with `cloudsql-proxy` container and configure requests/limits for each use case.	03/02/22	03/02/22	8hrs
2	Had a technical discussion with joe to complete the task	-	Completed	04/02/22	04/02/22	2hrs
3	CPU utilization monitoring in GCP Kubernetes container (i.e for one month)	-	Completed	05/02/22	06/02/22	5hrs
4	GIT installation	-	Completed	07/02/22	07/02/22	2hrs
5	SSH and HTTP Authentication	-	Completed	08/02/22	09/02/22	4hrs
6	GIT clone with cloud SQL-proxy repository	-	Completed	10/02/22	10/02/22	3hrs
7	GIT pull into the local repository	-	Completed	10/02/22	10/02/22	3hrs
8	values.yaml and deployment.yaml code updated as per CPU utilization monitoring	-	Completed	11/02/22	14/02/22	8hrs
9	created new branch INFRA 2652	-	Completed	14/02/22	14/02/22	8hrs
10	updated code commit to INFRA 2652 branch	-	Completed	14/02/22	14/02/22	8hrs
11	Code validation with joe and pull request to the main branch (i.e in the codefresh-config Github repo)	-	Completed	14/02/22	14/02/22	8hrs

Task S.no 2	Task name (Services update) services name	Description	Other Comments/Status	Task Start Date	Task End Date	Hours spent
1	Cloud sql proxy ticket number INFRA 2652	Review usage for CPU & memory in Cloud Monitoring metrics explorer. Look at the historical usage (1 month at least) and note the maximum amount of CPU and memory used by the cloudsql-proxy containers	The next step is to set reasonable requests/limits for cloudsqlproxy in the values.yaml file for the specific services that use cloudsqlproxy.	15/02/22	15/02/22	8hrs
2	Had a technical discussion with joe regarding the task	-	Completed	16/02/22	16/02/22	2hrs
3	Assigned 10 services to monitor CPU and memory usage and update it in values.yaml file	-	Completed	21/02/22	22/02/22	3 hrs
4	projects/platform/api-pa-frameconfig/chart/values.yaml	-	Completed	21/02/22	22/02/22	8hrs
5	projects/platform/api-ps-folder-migration/chart/values.yaml	-	Completed	17/02/22	17/02/22	8hrs
6	projects/platform/api-ps-kafka-sink-api/chart/values.yaml	-	Completed	21/02/22	22/02/22	8hrs
7	projects/platform/api-ps-kafka-sink-ms/chart/values.yaml	-	Completed	21/02/22	22/02/22	8hrs
8	projects/platform/api-ps-resource-migration/chart/values.yaml	-	Completed	18/02/22	18/02/22	8hrs
9	projects/platform/api/chart/values.yaml	-	Completed	21/02/22	22/02/22	8hrs
10	projects/platform/dataset/chart/values.yaml	-	Completed	23/02/22	24/02/22	8hrs
11	projects/platform/delivery-dispatch-api/chart/values.yaml	-	Completed	23/02/22	24/02/22	8hrs
12	projects/platform/infra-test/chart/values.dev.yaml	-	Completed	23/02/22	25/02/22	8hrs
13	projects/platform/megaphone-api/chart/values.yaml	-	Completed	23/02/22	25/02/22	8hrs

## Sheet2
S.NO	Projects	Cluster Name	Cluster Name2	Count
1	crux-dev-1	gusc1-dev-plat		36
2	crux-staging	gusc1-stg-plat (us-central1)	guse1-stg-plat (us-east1)	67
3	crux-199318 (crux)	gusc1-prd-plat (us-central1)	guse1-prd-plat (us-east1)	77
4	crux-data-stg	gusc1-stg-data (us-central1)		49
5	crux-data-prd	gusc1-prd-data (us-central1)	guse1-prd-data (us-east1)	88
6	crux-loaders-stg	gusc1-stg-loaders (us-central1)		25
7	crux-loaders-prd	gusc1-prd-loaders (us-central1)		27